## query (3)
PR | Title | Description | Status | Begin Project | Close Project | Item Type | Path
| POS Tactical Business Effort | Fund miscellaneous POS & In-store Customer-Facing development activities as well as small enhancement and maintenance efforts. | Tactical | 2021-01-04 | 2026-12-25 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010686 | POS central systems migration to Publix Private Cloud | This effort will complete the migration of the digital receipt, pay with the app (CPOS), WebPOS (bedside prescription delivery, and electronic raincheck solutions from standard virtual servers to the Publix Private Cloud (PPC). Deliverables in this effort includes creating TDDs, creating PPC servers, updating applications and performing certification testing. | Approved | 2023-01-02 | 2023-10-27 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010688 | Self-checkout maintenance release 2023 1H | This effort will focus on continued stabilization, improvements, and enhancements for the self-checkout solution. To improve our ADA accessibility and prepare for possible future regulations we will test an ADA compliant joystick that will allow customers to navigate the self-checkout screen without reaching or using the touch screen. Finally, we will pilot an updated product picklist on the self-checkout, the picklist is used by customers to look-up products without barcodes such as produce items. Picklist displays item description and an image. | Approved | 2023-01-30 | 2023-07-28 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010696 | StoreLine maintenance release 2023 | This effort will manage the StoreLine code deliveries including the annual release and multiple service packs. | Approved | 2023-02-06 | 2024-01-31 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010690 | NationsBenefits - development | This project is to develop a solution to support the NationsBenefits platform. This platform provides healthy food and OTC benefits to customers whose health plans are partnered with NationsBenefits. | Approved | 2023-05-29 | 2023-09-29 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010687 | Central refunds maintenance and enhancements | This project will complete design and development of a solution to integrate with the NationsBenefits program that allows Publix to accept those benefits. | Approved | 2023-05-29 | 2023-08-25 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010706 | IT Mod–In-store Accounting Sub-dept vouchers and Enhanced loan screen | This effort will develop the initial iteration of cash management features like sub-department vouchers and an enhanced loan screen. These features will allow associates to pick-up sub-department vouchers with more accurate descriptions and simplify the loan process from two steps to one. | Approved | 2023-05-29 | 2023-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010707 | IT Mod–Deli Combo, Liquor, Wine Promotions, and Quantity based Pricing | This effort will continue to design and develop iterations for the POS Anywhere promotions including deli combo, liquor, and wine as well as implement quantity-based pricing. | Approved | 2023-05-29 | 2023-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010703 | IT Modernization – POS Restrictions, and EFT Payments | This effort will include support for credit, debit, and gift card payments through the Payments as a Service system as well as implementing additional item sale restrictions. | Approved | 2023-05-29 | 2023-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010705 | IT Modernization - In-store acct. foundation to support the Cloud | This effort will begin the foundational work and initial iteration for cloud support of the in-store accounting data. | Approved | 2023-05-29 | 2023-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010704 | IT Modernization – Beta Shopper Features and Support Pay with App | This effort will implement support for Pay with the App, paper coupons, department sales, and remaining features necessary for the beta shopper pilot. | Approved | 2023-05-29 | 2023-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010695 | Self-checkout maintenance release 2023 2H | This effort will continue to implement business enhancements and bug fixes to the NCR self-checkout solution. | 5 Year Plan | 2023-07-03 | 2024-01-26 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010710 | IT Modernization - In-Store Acct to Cloud Integration | This effort will implement the data feed for in-store accounting activities being sent from each store, consumed into a corporate database, and finally landing in the Data Lake. | 5 Year Plan | 2023-08-14 | 2023-11-10 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010708 | IT Modernization - Deli combo discounts and wine/liquor promotions | This effort will add support to the POS for deli sub and dinner combo, wine/liquor, and other promotions requiring linked items. | 5 Year Plan | 2023-08-14 | 2023-11-10 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010709 | IT Modernization - Customer and cashier age restrictions | This effort will implement the sale restrictions for items requiring the customer or cashier to be of a certain age (non-Florida stores). | 5 Year Plan | 2023-08-14 | 2023-11-10 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010712 | Sales360 Data Aggregates and Quality Checkpoint | This effort will ensure all sales and accounting data loaded into the Data Lake meets the needs of the Store Accounting processes that will replace the Store Accounting Interface (SACTIF) weekly process. | 5 Year Plan | 2023-08-14 | 2023-11-10 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010711 | IT Modernization - Manual Pricing and Hardware Notifications | This effort will implement support for manual pricing (department sales) for items not found on the POS and hardware notifications (e.g., printer out of paper, printer paper jam, etc.). | 5 Year Plan | 2023-08-14 | 2023-11-10 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010694 | Central refunds maintenance and enhancements | This effort will continue to implement business enhancements and bug fixes for Central Refunds. | 5 Year Plan | 2023-08-28 | 2024-01-26 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010692 | Digital rain checks - pilot feedback | This effort will provide maintenance and enhancements based on learnings from the digital rain check pilot. Digital rain checks allow customers to receive rain checks digitally and automatically redeem after they self-identify at the POS. | 5 Year Plan | 2023-09-04 | 2024-03-29 | Item | sites/ISPOSCOS/Lists/Project Charters
| NationsBenefits - technical pilot | NationsBenefits - technical pilot | 5 Year Plan | 2023-10-02 | 2023-12-29 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010715 | IT Modernization - Back Office Reporting and In-store Accounting Azure Data | This effort will continue the implementation of the POS back office application which includes in-store reporting and begin work to send in-store accounting data to Azure. This Azure data will be initially used by the modern Store Accounting system. | 5 Year Plan | 2023-11-13 | 2024-02-09 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010714 | IT Modernization - Digital and paper coupons | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort will add support for digital (Inmar integration) and paper coupons at the POS. | 5 Year Plan | 2023-11-13 | 2024-02-09 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010713 | IT Modernization - Support scanning international product barcodes | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort will add support for scanning international product barcodes (e.g., EAN 8 and EAN 13) at the POS Checkout. | 5 Year Plan | 2023-11-13 | 2024-02-09 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010717 | IT Modernization - Sales360 Enterprise Data Feeds | This effort will cover the initial analysis needed to provide a data feed from Sales360 to third parties such as Inmar and Instacart. | 5 Year Plan | 2023-11-13 | 2024-02-09 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010716 | IT Modernization - Additional EFT Tenders and Save/Recall | This effort will implement support for additional EFT tenders such as EBT and eWIC as well as the save/recall functionality. | 5 Year Plan | 2023-11-13 | 2024-02-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| NationsBenefits - enable and stabilization | NationsBenefits - mass rollout | 5 Year Plan | 2024-01-01 | 2024-03-29 | Item | sites/ISPOSCOS/Lists/Project Charters
| Continuous package rollup 2024 | This effort will roll up any retail packages that have been massed but need to be incorporated into the base build packages. Once base build packages have been updated they will be turned over to the SBP for new stores resulting in our new stores opening with the newer features. | 5 Year Plan | 2024-01-29 | 2024-06-28 | Item | sites/ISPOSCOS/Lists/Project Charters
| Self-checkout maintenance release 2024 1H | This effort will continue to implement business enhancements and bug fixes to the NCR self-checkout solution. | 5 Year Plan | 2024-01-29 | 2024-06-28 | Item | sites/ISPOSCOS/Lists/Project Charters
| POS central systems maintenance | This effort will perform on-going maintenance and uplifts required on the applications and Publix Private Cloud (PPC) servers running the centralized POS systems (e.g., rain checks and CPOS for pay with the app). | 5 Year Plan | 2024-02-05 | 2024-06-28 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Back Office In-store Accounting Azure Data | This effort will continue the implementation of the POS back office application and the work to send in-store accounting data to Azure. This Azure data will be initially used by the modern Store Accounting system. | 5 Year Plan | 2024-02-12 | 2024-05-10 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Accounting Azure Data Enhancements 2024 Q1/Q2 | This effort will implement maintenance and enhancements to the In-Store Accounting Azure data pilot. | 5 Year Plan | 2024-02-12 | 2024-05-10 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - POS Partial Authorizations and Discounts | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This is the effort to implement partial authorizations for EFT payments and discounts (e.g., Sr. Discount). Partial authorization will be completed in time for the Q1 2024 customer pilot. | 5 Year Plan | 2024-02-12 | 2024-05-10 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Non-FL Discounts | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort will develop support of transaction discounts offered outside of Florida. | 5 Year Plan | 2024-02-12 | 2024-05-10 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Implement Money Services Support | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort develop support for money services (ringing up Western Union) on the POS Checkout. | 5 Year Plan | 2024-02-12 | 2024-05-10 | Item | sites/ISPOSCOS/Lists/Project Charters
| Healthy Saving maintenance release | This project is a place holder to implement enhancements and bug fixes to solution that support the NationsBenefits and Solutran platforms. These platforms provides benefits to customers whose health plans are partnered with NationsBenefits and Solutran. The timeline for this project will be updated based on the implementation project. | 5 Year Plan | 2024-04-01 | 2024-09-27 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Back Office Configuration 2024 Q2/Q3 | This effort will begin the work to develop in-store user controlled configuration to support the POS Anywhere checkout and back office functionality. In-store configurations includes updating the store manager's name that appears on the receipt. | 5 Year Plan | 2024-05-13 | 2024-08-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Accounting Azure Data Enhancements 2024 Q2/Q3 | This effort will implement maintenance and enhancements to the In-Store Accounting Azure data pilot. | 5 Year Plan | 2024-05-13 | 2024-08-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - POS Self-checkout Initial Iteration | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort is the initial work to implement the self-checkout user interface for POS Anywhere. | 5 Year Plan | 2024-05-13 | 2024-08-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Lottery Integration | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort will complete research to determine if there is a business need for integration with the state lottery system. | 5 Year Plan | 2024-05-13 | 2024-08-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - User Authorization with OAuth | This Project will begin the work to develop POS Anywhere checkout integration with OAuth. OAuth is the solution that will be used to authenticate cashier sign-on to the checkout application. | 5 Year Plan | 2024-05-13 | 2024-08-09 | Item | sites/ISPOSCOS/Lists/Project Charters
PR010691 | Support FSA tender with pay with app | This project will implement enhancements to the POS to support FSA tenders via the Publix app. With this effort, customers will be able to add FSA cards to their Publix wallet and have the ability to pay at the POS with the Publix app. During this project we will also support enhancements and improvements to the digital gift cards solution based on customer feedback received during rollout. | 5 Year Plan | 2024-06-03 | 2025-03-28 | Item | sites/ISPOSCOS/Lists/Project Charters
| Central refunds maintenance | This effort will continue to stabilize Central Refunds. | 5 Year Plan | 2024-06-03 | 2025-02-28 | Item | sites/ISPOSCOS/Lists/Project Charters
| Self-checkout maintenance release 2024 2H | This effort will continue to implement business enhancements and bug fixes to the NCR self-checkout solution. | 5 Year Plan | 2024-07-01 | 2025-01-31 | Item | sites/ISPOSCOS/Lists/Project Charters
| Rain check maintenance release | This effort will continue to implement business enhancements and bug fixes to the rain check system. | 5 Year Plan | 2024-07-01 | 2024-12-27 | Item | sites/ISPOSCOS/Lists/Project Charters
| POS maintenance release 2024 2H | This effort will continue to implement business enhancements and bug fixes to the StoreLine POS application. | 5 Year Plan | 2024-07-01 | 2024-12-27 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Back Office Configuration 2024 Q3/Q4 | This effort will complete the implementation of in-store user controlled configuration to support the POS Anywhere checkout and back office functionality. In-store configurations includes updating the store manager's name that appears on the receipt. | 5 Year Plan | 2024-08-12 | 2024-11-08 | Item | sites/ISPOSCOS/Lists/Project Charters
| Sale / Accounting Cloud Data Enhancements 2024 Q3/Q4 | This effort will complete maintenance and enhancements to the Sales360 and In-Store Accounting data system. | 5 Year Plan | 2024-08-12 | 2024-11-08 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Initial Back Office Accounting Integration | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort will integrate the checkout with the modern back office accounting application. | 5 Year Plan | 2024-08-12 | 2024-11-08 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Specialty Register UI | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort will complete work to support specialty lanes (e.g., pharmacy) user interfaces. | 5 Year Plan | 2024-08-12 | 2024-11-08 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Initial Starbuck and POURS UI | This project is part of the POS modernization and is one of a series of efforts that will develop core components to support the in-store checkout. This effort will complete research and development for the checkout user interfaces for Starbucks and POURS venues. | 5 Year Plan | 2024-08-12 | 2024-11-08 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - Back Office Stabilization | This project will implement enhancements and bug fixes for the modernized back office functionality pilot. | 5 Year Plan | 2024-11-11 | 2025-02-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| Sale / Accounting Cloud Data Enhancements 2024 Q4/Q1 2025 | This effort will complete maintenance and enhancements to the Sales360 and In-Store Accounting data system. | 5 Year Plan | 2024-11-11 | 2025-02-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - POS Checkout Stabilization 2024 Q4 | This project is part of the POS modernization and is one of a series of efforts that will develop enhancements and bug fixes based on feedback and production pilot results of the in-store checkout. | 5 Year Plan | 2024-11-11 | 2025-02-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - POS Checkout Enhancements | This project is part of the POS modernization and is one of a series of efforts that will develop enhancements and bug fixes based on feedback and production pilot results of the in-store checkout. | 5 Year Plan | 2024-11-11 | 2025-02-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| IT Modernization - POS Checkout Enhancements | This project is part of the POS modernization and is one of a series of efforts that will develop enhancements and bug fixes based on feedback and production pilot results of the in-store checkout. | 5 Year Plan | 2024-11-11 | 2025-02-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| Self-checkout on-going maintenance releases | This effort is a place holder for our five year plan for on-going maintenance that will need to be performed for the NCR self-checkout solution to implement business enhancements and bug fixes. | 5 Year Plan | 2025-02-03 | 2028-01-28 | Item | sites/ISPOSCOS/Lists/Project Charters
| Sales Interfaces Enhancements Q1 2025 | This project will implement enhancements and bug fixes for the sales interfaces (Sales360 and In-Store Accounting Data) | 5 Year Plan | 2025-02-07 | 2025-05-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Begin Rollout | This project will begin the rollout of the POS Anywhere Checkout product as well as continue to implement enhancements and bug fixes | 5 Year Plan | 2025-02-07 | 2025-05-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| Back Office Maintenance and Enhancements Q1 2025 | This project will implement enhancements and bug fixes for the Back Office application | 5 Year Plan | 2025-02-07 | 2025-05-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Enhance and Stabilize Q1 2025 (Feature Team 2) | This project will implement enhancements and work toward stabilization of the POS Anywhere Checkout effort | 5 Year Plan | 2025-02-07 | 2025-05-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Enhance and Stabilize Q1 2025 (Feature Team 3) | This project will implement enhancements and work toward stabilization of the POS Anywhere Checkout effort | 5 Year Plan | 2025-02-07 | 2025-05-09 | Item | sites/ISPOSCOS/Lists/Project Charters
| Sales Interfaces Enhancements Q2 2025 | This project will implement enhancements and bug fixes for the sales interfaces (Sales360 and In-Store Accounting Data) | 5 Year Plan | 2025-05-12 | 2025-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Continue Rollout Q2 2025 | This project will continue the rollout of the POS Anywhere Checkout product as well as continue to implement enhancements and bug fixes | 5 Year Plan | 2025-05-12 | 2025-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
| Back Office Maintenance and Enhancements Q2 2025 | This project will implement enhancements and bug fixes for the Back Office application | 5 Year Plan | 2025-05-12 | 2025-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Enhance and Stabilize Q2 2025 (Feature Team 2) | This project will implement enhancements and work toward stabilization of the POS Anywhere Checkout effort | 5 Year Plan | 2025-05-12 | 2025-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Enhance and Stabilize Q2 2025 (Feature Team 3) | This project will implement enhancements and work toward stabilization of the POS Anywhere Checkout effort | 5 Year Plan | 2025-05-12 | 2025-08-11 | Item | sites/ISPOSCOS/Lists/Project Charters
| Sales Interfaces Enhancements Q3 2025 | This project will implement enhancements and bug fixes for the sales interfaces (Sales360 and In-Store Accounting Data) | 5 Year Plan | 2025-08-09 | 2025-11-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Continue Rollout Q3 2025 | This project will continue the rollout of the POS Anywhere Checkout product as well as continue to implement enhancements and bug fixes | 5 Year Plan | 2025-08-09 | 2025-11-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| Back Office Begin Deprecation of StoreLine | This project will continue to implement enhancements and bug fixes for the Back Office application as well as begin the work necessary to deprecate StoreLine | 5 Year Plan | 2025-08-09 | 2025-11-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Enhance and Stabilize Q3 2025 (Feature Team 2) | This project will implement enhancements and work toward stabilization of the POS Anywhere Checkout effort | 5 Year Plan | 2025-08-09 | 2025-11-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Enhance and Stabilize Q3 2025 (Feature Team 3) | This project will implement enhancements and work toward stabilization of the POS Anywhere Checkout effort | 5 Year Plan | 2025-08-09 | 2025-11-07 | Item | sites/ISPOSCOS/Lists/Project Charters
| Sales Interfaces Enhancements Q4 2025 | This project will implement enhancements and bug fixes for the sales interfaces (Sales360 and In-Store Accounting Data) | 5 Year Plan | 2025-11-10 | 2026-02-06 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Complete Rollout | This project will complete the rollout of the POS Anywhere Checkout product as well as continue to implement enhancements and bug fixes | 5 Year Plan | 2025-11-10 | 2026-02-06 | Item | sites/ISPOSCOS/Lists/Project Charters
| Back Office Continue Deprecation of StoreLine | This project will continue to implement enhancements, bug fixes, and work necessary to deprecate StoreLine for the Back Office application | 5 Year Plan | 2025-11-10 | 2026-02-06 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Enhance and Stabilize Q4 2025 (Feature Team 2) | This project will implement enhancements and work toward stabilization of the POS Anywhere Checkout effort | 5 Year Plan | 2025-11-10 | 2026-02-06 | Item | sites/ISPOSCOS/Lists/Project Charters
| Checkout Enhance and Stabilize Q4 2025 (Feature Team 3) | This project will implement enhancements and work toward stabilization of the POS Anywhere Checkout effort | 5 Year Plan | 2025-11-10 | 2026-02-06 | Item | sites/ISPOSCOS/Lists/Project Charters